## KT Plan
[7 empty] | Planned |  |  | Actual
| KT Area | Topics | Do we have this Document / Artifact? | Responsibility (FROM) | Responsibility (TO) | Transition Methodology | Start Date | End Date | Duration (Days) | Start Date | End date | Duration (Days) | Completion Status | Comments
|  |  | Yes/No |  |  | Email/Webex/Physical
| Account Overview | Horizon Business Overview
| Healthcare Overview | Introduction to Healthcare
| Claims Overview | Claim Processing
Step 1 | VM setup and access to PROD and PRE PROD
VM access
RSA Token
Development Server/Web app access
Database Access
Deployment Environment access
Step 2 | Technical Transition
|  | Open Connect - Overview |  | Abhinaya/Aarathi | Priya & Manusha |  | 2022-01-24 | 2022-02-04 |  |  |  |  | Completed | Explained about the usage of ConnectIQ tools and how it interacts with .NET and NASCO Exapained how the robot will work and reduce the manual intervention using the ConnectIQ tool.
|  | Open Connect - Transaction Editor - Panels |  | Abhinaya/Aarathi | Priya & Manusha |  | 2022-01-24 | 2022-02-04 |  |  |  |  | Completed | Explained about : What is transaction how to create a new transaction, All the statements like (assign,if,while,perform,setstate)..etc Functions Creation for local variables and arrays Inputs and Outputs Arthimetic operattors Conditional operators Session View Panels Editor Script Editor Controller entry
|  | Open Connect - Deployment & Troubleshooting |  | Abhinaya/Aarathi | Priya & Manusha |  | 2022-01-24 | 2022-02-04 |  |  |  |  | Completed | Explained how to do the deployment and how to debug the claim in connectIQ . Navigated with one sample claim Explained how to navigate to segment and come back to EEC Explained how to updated values in NASCO and how to retrieve values from NASCO.
|  | Open Connect -How to Monitor Jobs in Open Connect |  | Abhinaya/Aarathi | Priya & Manusha |  | 2022-01-24 | 2022-02-04 |  |  |  |  | In Progress
|  | Open Connect -Troubleshoot issues |  | Abhinaya/Aarathi | Priya & Manusha |  | 2022-01-24 | 2022-02-04 |  |  |  |  | Completed | Explained how to navigate to segment and come back to EEC Explained how to updated values in NASCO and how to retrieve values from NASCO. Explained how to use funtion and how to create local variable and arrray and the usage debug statements.
|  | Open Connect -Where to Check for Results. Action to be taken for alerts |  | Abhinaya/Aarathi | Priya & Manusha |  | 2022-01-24 | 2022-02-04 |  |  |  |  | In Progress
|  | NASCO KT,segment details and Claim processing in NASCO |  | Abhinaya/Aarathi | Priya & Manusha |  | 2022-01-24 | 2022-02-04 |  |  |  |  | In Progress | Explained how to open the claims in NASCO How to check the header and line level details How to navigate Segment and how to come back to EEC Shared the document Pending items to explain on the shortcuts keys,how to override and deny
Step 3 | Shadowing /Reverse shadowing
|  | Help and Validation of Understanding / Resolution |  | Onsite |  |  | 2022-02-07 | 2022-02-07
Shadowing
Step 4 | Steady State |  |  | Onsite |  |  | 2022-02-08 | [5 empty] | To Be Started

## Notes
Sharepoint Details